# Bodax SACCO Management System Project Plan

# 1. Plan Overview

This project plan covers the remaining 6-week completion period for Bodax SACCO Management System. The plan focuses on turning the current working prototype into a cleaner, better documented, field-ready SACCO platform for boda boda riders, treasurers, and chairmen.

The plan is based on:

- The current React, Express, and PostgreSQL codebase.

- Existing modules for members, savings, loans, withdrawals, dashboards, and reports.

- Field-test feedback from Mile 4 Boda Boda Stage in Mbarara.

- The need for clear project documentation, user guidance, testing, and deployment readiness.

# 2. Project Duration

Total duration: 6 weeks.

Suggested timeline:

- Week 1: Documentation baseline and critical data-entry safety.

- Week 2: Authentication and member trust improvements.

- Week 3: Savings, statements, withdrawals, and mobile usability.

- Week 4: Loans, repayments, reminders, and chairman visibility.

- Week 5: Reporting, testing, deployment hardening, and training materials.

- Week 6: User acceptance testing, fixes, final documentation, and handover.

# 3. Project Objectives for the 6 Weeks

- Complete clear project proposal, documentation, and implementation plan.

- Improve field usability for boda boda riders using small Android phones.

- Reduce financial data-entry mistakes in savings, loans, and withdrawals.

- Strengthen phone-first member access and account identity.

- Improve loan request, approval, repayment, and overdue tracking.

- Prepare dashboards and reports for real SACCO committee use.

- Test the system end to end before pilot rollout.

- Deliver final handover documentation.

# 4. Work Breakdown by Week

## Week 1: Documentation Baseline and Critical Safety

Main goal: Establish clear documentation and fix the highest-risk financial workflow issue.

Planned activities:

- Prepare project proposal, project documentation, and project plan.

- Review existing modules and confirm system scope.

- Document current business rules for savings, loans, withdrawals, and reports.

- Add confirmation prompts before important financial submissions:

- Record savings.

- Approve loan request.

- Reject loan request.

- Issue loan.

- Record repayment.

- Approve withdrawal.

- Reject withdrawal.

- Ensure confirmation text shows member name, member number, amount, and action.

- Review current validation messages and make them clearer for field users.

- Create a testing checklist for critical financial workflows.

Deliverables:

- Project proposal document.

- Project documentation document.

- Project plan document.

- Confirmation workflow design.

- Updated financial action screens.

- Week 1 test notes.

Acceptance criteria:

- Documentation exists and reflects the current system.

- Treasurer cannot accidentally submit major financial actions without seeing a confirmation message.

- Confirmation messages use human-readable member details, not only IDs.

## Week 2: Authentication and Member Trust

Main goal: Make login and member identity easier and more trustworthy for riders.

Planned activities:

- Improve login screen wording so riders understand they can use phone number or email where supported.

- Prepare phone-number-first login flow.

- Review member signup and member credential assignment.

- Display member full name and member number prominently on the member dashboard.

- Add or prepare space for member photo/avatar if required.

- Improve profile page to clearly show SACCO identity details.

- Make password change flow clearer.

- Document recommended OTP integration approach for future SMS login.

- Review authentication and authorization edge cases.

Deliverables:

- Improved login and member identity screens.

- Updated member dashboard identity header.

- Authentication notes in documentation.

- OTP integration recommendation.

Acceptance criteria:

- A member can clearly identify that the dashboard belongs to them.

- The login experience is less email-dependent in wording and flow.

- Profile information is understandable to ordinary SACCO members.

## Week 3: Savings, Statements, Withdrawals, and Mobile Usability

Main goal: Improve day-to-day SACCO transactions and small-screen use.

Planned activities:

- Update UGX amount inputs to accept values such as `50000` and `50,000`.

- Normalize formatted amounts before API submission or validation.

- Improve validation messages for amount fields.

- Improve savings record form layout and field labels.

- Add deposit success details that can act as a simple receipt summary.

- Improve member statements for mobile screens by using responsive cards or better table behavior.

- Improve withdrawal request and withdrawal review screens.

- Confirm statement records show savings, loan repayments, and withdrawals clearly.

- Test on narrow mobile widths representing low-cost Android phones.

Deliverables:

- Improved amount input handling.

- Mobile-friendly statements view.

- Clear savings success/receipt summary.

- Improved withdrawal workflow screens.

- Week 3 mobile test notes.

Acceptance criteria:

- Users can enter `50,000` without validation confusion.

- Statements are readable on small screens.

- Savings and withdrawal workflows use clearer member-facing language.

## Week 4: Loans, Repayments, Reminders, and Chairman Visibility

Main goal: Strengthen the SACCO loan workflow and oversight experience.

Planned activities:

- Review loan eligibility messages and simplify loan terminology.

- Replace confusing terms where needed:

- Installment count becomes Number of payments.

- Principal becomes Amount borrowed where user-facing.

- Improve loan request status display for members.

- Improve loan approval/rejection screens for treasurer.

- Ensure active, completed, and overdue loans display clearly.

- Improve repayment recording workflow.

- Review overdue loan status refresh behavior.

- Improve chairman view of defaulters and overdue loans.

- Ensure chairman and treasurer views show member names and member numbers instead of technical IDs.

- Prepare SMS or WhatsApp notification event list:

- Deposit recorded.

- Loan approved.

- Loan rejected.

- Loan due soon.

- Loan overdue.

- Withdrawal approved.

Deliverables:

- Clearer loan forms and loan status pages.

- Improved overdue loan and defaulter visibility.

- Notification event plan.

- Week 4 loan workflow test notes.

Acceptance criteria:

- Members understand loan request fields and status.

- Treasurer can approve/reject and record repayments confidently.

- Chairman can identify overdue loans by member name and amount.

## Week 5: Reporting, Testing, Deployment, and Training Materials

Main goal: Stabilize the system and prepare it for a controlled pilot.

Planned activities:

- Verify treasurer dashboard totals.

- Verify chairman dashboard totals.

- Verify analytics for top savers, defaulters, collections, income, and expenditure.

- Add or document report interpretation notes for SACCO leaders.

- Test all major API endpoints.

- Test role-based access for Member, Treasurer, and Chairman.

- Review deployment environment variables.

- Confirm health check endpoint works.

- Review Render and Vercel deployment setup.

- Prepare training materials:

- Treasurer quick guide.

- Member quick guide.

- Chairman quick guide.

- Pilot support checklist.

Deliverables:

- Tested dashboards and reports.

- Deployment checklist.

- User training guides.

- Role-based testing checklist.

- Week 5 test report.

Acceptance criteria:

- Dashboard numbers match expected database records.

- Each role can access only the correct screens.

- Deployment steps and environment variables are documented.

- Training guides are ready for SACCO users.

## Week 6: User Acceptance Testing, Final Fixes, and Handover

Main goal: Complete final validation and prepare for SACCO committee sign-off.

Planned activities:

- Conduct full end-to-end testing:

- Register member.

- Assign login.

- Record savings.

- View member dashboard.

- Request loan.

- Approve loan.

- Record repayment.

- Track overdue/completed status.

- Request withdrawal.

- Approve withdrawal.

- View reports.

- Conduct user acceptance testing with sample users.

- Fix defects discovered during final testing.

- Finalize project proposal, documentation, and plan.

- Prepare final handover package.

- Prepare pilot rollout recommendations.

- Record known limitations and future enhancements.

Deliverables:

- Final tested application.

- Final project documentation.

- Final user guides.

- UAT report.

- Handover notes.

- Pilot rollout recommendation.

Acceptance criteria:

- Core SACCO workflows run successfully end to end.

- Critical field-test issues are fixed or clearly documented for the next phase.

- SACCO committee can review the project with clear documents and test evidence.

# 5. Documentation Plan

Documentation will be maintained throughout the 6 weeks instead of being written only at the end.

| Week | Documentation Work |
| --- | --- |
| Week 1 | Create proposal, project documentation, and project plan; document current modules and business rules |
| Week 2 | Update authentication, member identity, and profile documentation |
| Week 3 | Add savings, statement, withdrawal, mobile usability, and receipt notes |
| Week 4 | Add loan workflow, repayment, eligibility, overdue loan, and notification documentation |
| Week 5 | Add reporting, deployment, testing, and user training guides |
| Week 6 | Finalize all documents, add UAT findings, known limitations, and handover notes |

Required documents by completion:

- Project Proposal.

- Project Documentation.

- Project Plan.

- Treasurer User Guide.

- Member User Guide.

- Chairman User Guide.

- Deployment Checklist.

- Testing and UAT Report.

- Handover Notes.

# 6. Testing Plan by Week

| Week | Testing Focus |
| --- | --- |
| Week 1 | Confirmation prompts and financial action safety |
| Week 2 | Login, role access, member identity, profile, password changes |
| Week 3 | Savings entry, amount validation, statements, withdrawals, mobile layout |
| Week 4 | Loan eligibility, requests, approvals, repayments, overdue status |
| Week 5 | Reports, dashboards, API endpoints, deployment configuration |
| Week 6 | Full end-to-end testing and user acceptance testing |

# 7. Roles and Responsibilities

| Role | Responsibility |
| --- | --- |
| Project Lead | Coordinate weekly tasks, track completion, approve scope changes |
| Frontend Developer | Implement React pages, forms, responsive layouts, and role screens |
| Backend Developer | Implement API logic, validation, database queries, and business rules |
| Database Lead | Maintain schema, indexes, seed data, and data integrity |
| Tester | Validate workflows, mobile views, role access, and field-test fixes |
| SACCO Treasurer | Provide operational feedback and test real savings/loan workflows |
| SACCO Chairman | Validate reports, defaulters, arrears, and governance requirements |
| Member Representatives | Test usability from the rider perspective |

# 8. Priority Backlog

## Critical

- Confirmation prompts before financial actions.

- Phone-friendly login and account identification.

- UGX amount fields that accept comma formatting.

- Mobile-readable statements and loan tables.

- Member names displayed clearly in treasurer and chairman views.

## High Priority

- SMS or WhatsApp notification integration plan.

- Deposit receipt or shareable transaction proof.

- Improved loan terminology for riders.

- Overdue loan dashboard for chairman.

- Better role-specific training materials.

## Medium Priority

- Local language support for common labels and errors.

- Offline mode planning.

- Optional member photo/avatar.

- More advanced audit logs.

- Exportable reports.

# 9. Risk Management

| Risk | Likelihood | Impact | Response |
| --- | --- | --- | --- |
| Scope grows beyond 6 weeks | Medium | High | Keep v1 focused on core SACCO workflows and move extras to future backlog |
| SMS/OTP integration takes longer than expected | Medium | Medium | Document provider plan first and implement only if core work is stable |
| Database errors affect financial records | Low | High | Use transactions, validation, confirmation prompts, and careful testing |
| Users struggle with English terminology | Medium | Medium | Simplify wording first, then plan Runyankore translations |
| Mobile layouts fail on small devices | Medium | High | Test weekly at narrow widths and convert complex tables to cards |
| Deployment environment variables are misconfigured | Medium | Medium | Maintain a deployment checklist and verify `/health` endpoint |

# 10. Milestone Summary

| Milestone | Target Week | Output |
| --- | --- | --- |
| Documentation baseline complete | Week 1 | Proposal, documentation, plan |
| Critical financial safety improved | Week 1 | Confirmation prompts |
| Member trust improvements complete | Week 2 | Better login wording and identity display |
| Transaction workflows improved | Week 3 | Savings, statements, withdrawals, amount inputs |
| Loan workflow strengthened | Week 4 | Loan requests, approvals, repayments, overdue visibility |
| Reports and deployment validated | Week 5 | Dashboards, analytics, deployment checklist |
| Final UAT and handover complete | Week 6 | Final docs, test report, pilot recommendation |

# 11. Definition of Done

A feature or document is considered done when:

- It matches the agreed SACCO workflow.

- It is understandable to its intended user role.

- It has been tested with valid and invalid inputs.

- It handles errors clearly.

- It does not expose another member's private data.

- It works on desktop and mobile screen sizes.

- Its relevant documentation has been updated.

# 12. Final Handover Package

At the end of week 6, the project should include:

- Working deployed application.

- Source code in the repository.

- Database schema and setup instructions.

- Project proposal.

- Project documentation.

- Project plan.

- User guides for Member, Treasurer, and Chairman.

- Deployment checklist.

- Testing and UAT report.

- Known issues and future enhancement list.

- Pilot rollout recommendation for the SACCO committee.